NARRATIVE REPORT

Project title and number: REFORM/IM2022/009 - Further Development of the Innovative Capacity of the Public Sector of Latvia (22LV21)

- Overall Summary of the project(s)

This project aimed to enhance the capacity for innovation across national and municipal public administrations in Latvia, with a focus on how innovation can address key societal governance problems. The project aimed to equip the State Chancellery (including the Innovation Lab) to steer and coordinate innovation efforts including empowering the public sector to use innovation to improve the wellbeing of the Latvian public through an assessment of innovative capacity, proposed strategy for public sector innovation, building capacity for innovation measurement and capacity building on two key innovation methods (policy design and strategic foresight).

- Outputs delivered and corresponding outcomes

The key components of this project included: - An innovative capacity assessment of the current system (national and municipal level) based on a literature review, interviews, national and local level workshops (five total) and a survey of municipal, non-governmental and governmental actors (1600+ responses total). This assessment provided an evidence-based understanding of the key strengths, weaknesses and opportunities for impactful public sector innovation in Latvia, equipping decision-makers with intelligence to make strategic decisions on innovation investments. - A proposed national innovative capacity strategy / action plan was co-created under OECD leadership through co-creation workshops at the national and municipal levels and bilateral meetings with key strategy action owners. This strategy aims to improve public wellbeing in Latvia through more and better innovation in the public sector. To support this goal, the strategy aims to improve the effectiveness, impact and continuity of the Latvian Innovation Lab and introduce a more systemic approach to innovation in Latvia. - The strategy proposal was accompanied by a monitoring framework to help those implementing the strategy measure and understand the impact of these efforts. This monitoring framework can equip actors involved in the strategy implement to demonstrate the impact of investments made in innovation. - Delivery of innovative capacity method prototypes on policy design and strategic foresight, applied to concrete policy issues including affordable housing in the Cēsis municipality, implementation of the New European Bauhaus in Latvia and visioning and resilience building of the Latvian Innovation Lab and Expert Network.

- Project activities

This project included extensive research and engagement activities: - Kick-off workshop and event held on 1 February 2023. - Blogs, LinkedIn Posts, Tweets and a webpage disseminating insights of the project. - An extensive literature review. - In person and virtual interviews with key actors in the public sector. - 10+ workshops with national and municipal actors to gather evidence for the assessment report and co-create a strategy for public sector innovation. - Three survey modules, reaching over 1600+ public servants at the national and municipal levels and actors in the non-governmental sector. - A launch event for the assessment report in October 2023. - Bilaterial meetings with key actors in the innovation space - A policy design train-the-trainer course. - Pilot methodology on policy design testing through sprints with OECD support on 1) attractiveness of the Cēsis municipality and 2) implementation of the New European Bauhaus in Latvia. These were run collaboratively with the OECD and Innovation Lab to build the lab’s capacity in these methods. - Facilitation of a strategic foresight workshop with the innovation network in Kuldiga in January 2024 directly testing visioning methods on the vision of the innovation network (including visioning, stress testing and backcasting). - Workshop with the innovation network in September 2024. - Bootcamp session using strategic foresight methods (pre-morteming) with the innovation lab in September 2024. - Online workshops held periodically with the Innovation Lab leveraging strategic foresight methods for the Lab’s visioning, operations and governance approach. - Theory of change and monitoring framework development workshops. - Development and provision of an extensive strategy evaluation and monitoring document provided to the Latvian Lab. - Ad-hoc support provided to Latvian Lab through regular meetings with OECD external consultant experts. - Meetings held between Latvian Lab and OECD in October 2024 to build capacity for monitoring and evaluation. - Provision of a guide on innovation evaluation, targeted to the Latvian experience.

- Difficulties encountered

This project had a slow start due to staff turnover in the Latvian Innovation Lab. The only staff member of the lab, and the head of the responsible unit both left the Chancellery in the first six months of the project. Consequently, the project was extended to ensure successful delivery.

- Progress on the implementation of the Visibility and Communication Plan

Communications and dissemination activities have been integral to socialising the innovative capacity assessment and ongoing activities through this project. A number of blogs have been produced on the OECD OPSI website, a webpage published on the OECD OPSI website featuring the project work and use of social media channels (notably LinkedIn) to disseminate efforts. A project factsheet and summary video were also produced to disseminate the project.

- Work plan for the following period (when relevant)

While this project has come to a conclusion, the Latvian State Chancellery Innovation Lab has gained considerable capacity to manage public sector innovation initiatives in Latvia. Moreover, the Innovation Lab staff are regular members of OECD working groups and the national contact point network on public sector innovation, connecting them to the OECD’s work in this area and linking the Lab to global experts.